Blackberry Jam Committee

Regular Meeting

Tuesday, , 2026, 6:00 PM Fire Department

Regular Meeting Agenda

- Call to Order/ Roll Call 6:02 pm

Meesa Anders __X_ Lonna Bennett _X__ Rusie Ackland ___ Ben Anders __X_ George Wild __X_

- Approval of Agenda First Lonna, Second Ben

- Approval of Meeting Minutes First Lonna, Second George

- BBJ Meeting Minutes February 10, 2025

Volunteer members: Max, Dennis, Jeninne

Old Business

- Craft Booths- 18 vendors, no increase in fees.

- Kids’ Corner- Lyn and Jessica will be in charge of set up and teardown.

- Food Vendors- 2 vendors have signed up, no increase in fees.

- Car Jam- 5 cars have signed up. Ray will make the trophies in the school’s wood shop. Kennette has reserved the football field.

- Parade-Lonna and George had a meeting with Lon and came up with a new parade route. Cars will line up on D St.; the parade will go from D St to 6th St. then to Moss St. The parade will end at Main St and Moss St.

- Grand Marshall- TBD

- Grease Pole & CIH- Tim

- Sponsors- Sam sent out multiple letters to sponsors last week.

- Horseshoes-Cornhole- Brad will oversee horseshoes on Friday night. We are looking for a new person to oversee cornhole.

- Electrical- Dennis talked with Star Rentals and Sales and secured power boxes and cords. The city is looking at adding a power outlet to the food vendor area.

- Entertainment- 2 bands are under contract.

- Bathrooms/Porta Potties/Handwash- We need to add two ADA approved toilets for the car jam at the football field.

- VJ- Rustie will be the VJ, her back up will be Sam and Sam’s back up will be Don.

- Caboose Tours (ED and Laura)-

- Schedule/Ads/Program/Map- When the weather is nicer and we have a sunny day the fire truck will be pulled out and a picture will be taken to go on the tee shirts and posters.

- Trash/Recycling- Sam has been in contact with Santi Pac.

- Local Business Involvement- Meesa has been talking with local business about donating to the BBJ.

- Crawl, Drag, Squirt-

- Dunk Tank- Meesa will contact the school to see if they are going to do a dunk tank.

- First Aid- Dennis, Jeninne and Meesa.

- School Involvement- Ray will be in Eastern Oregon during the BBJ. The assistant coach will be available to work for the BBJ with the football boys.

- Church- Tony and Tina

- Canines- Meesa will contact the officer.

- Security- George will contact the security company. We will want coverage starting at 8am on Friday morning and an extra person to cover the car jam on Saturday.

- 3 on 3 Basketball- Mike Neet

- Fire Truck- Ben is working on the fire truck.

New/Other Business

Adjourn the Regular Meeting 7:08 pm